## Sheet1
https://dev.azure.com/orionadvisor/OAT/_workitems/edit/216901 |  | Developer - Prerna sood |  |  |  | Developer`s remark
Test Case | Expected Results | Actual Results | Status | Messages
Firm 1100 -> model grid -> select Approved model ID 814 -> Export model for bulk edit -> Import file without any change. | file must be imported successfully if no changes made in Exported model file. | Working as Expected. | PASS
Firm 1100 -> model grid -> select model with status Waiting for approval or Draft -> model ID 814 -> Export model for bulk edit -> Import file without any change. | File should not be exported as model status is waiting for approval or draft. | Working as Expected. | PASS
Firm 141600 -> model grid -> select all model -> Export model for bulk edit -> open Exported model file. | Exported model file must have details of every category , class and security set node. | Not working as Expected. | FAIL | Reproduced in Firm 22700 > Select all models > Export model for Bulk edit > Open Exported mode file. |  | model is edited from UI
Firm 141600 -> model grid -> select all model -> Export model for bulk edit -> Import file without any change. | file must be imported successfully if no changes made in Exported model file. | Working fine now. | PASS | Model has only one SS and that Security Set is present with same name and Different description in SS table, while exporting model Every SS with same name exported in file. |  | on importing file it gives error in model id 52,52,65 after investigating we found problem is originate from modelId 52 and that model is editied from UI assign dto to Rahul
Firm 141600 -> model grid -> select model ID 72 -> Export model for bulk edit -> Import file without any change. | Approved model must be Exported successfully. | Working fine now. | PASS | Getting 422 Error when Exporting model file. "Update process is in progress. Please try after some time." |  | not reproducing
Firm 1100 -> model ID 899 -> Export model for bulk edit -> import file without any change. | file must be imported successfully if no changes made in Exported model file. | Not working as Expected. | FAIL | 2nd MAC validations failed. |  | not reproducing
Firm 1100 -> Models grid -> select 50 models -> Actions -> Export model for bulk edit -> "Getting Error 422 when exporting models." | [5 empty] | no error working fine.
Firm 1600 -> Models grid -> Select model ID 270 , 283 -> Actions -> Export model for bulk edit -> Import file without any change -> "Getting 2nd MAC validation failed." | [5 empty] | file imported successfully
Firm 1600 -> Models grid -> Select all model -> Actions -> Export model for bulk edit -> "Getting Error 422 when exporting models." | [5 empty] | exported successfully
Firm 1100 -> Models grid -> select models ( 776 to 1159 ) -> Exprt models for bulk edit -> Import file without any change -> create model. | file must be imported successfully if no changes made in Exported model file. | Not working as Expected. | FAIL | securitySet Name OR Id is not matching with any existing securitySets : Model ID 824 Node: MB1 is used at multiple places and its structure doesn't match : Model ID 1024 |  | data issue
Firm 1100 -> Models grid -> select models ID ( 1157 , 1158 , 1159 ) -> Export model for bulk edit -> open Exported model File -> Edit model name to TEST Model -> Model name must be Same -> Model namespace should be different for every model -> Save file -> Import model. | Total count and success count must be 3 for imported file. | Working fine now. Firm 2100. | PASS | File is successfully Imported > changes reflected in 3 models > But In model "Import logs" it is showing Total count and Success count = 1. |  | Fixed
Firm 1100 -> Models grid -> Select model ID 1054 , 1060 -> Export model for Bulk edit -> Import file without any change -> Getting Import Error " Model and Security set isDynamic flag does not match. Model ID : 1060 " |  | Working fine now. | PASS | Failed to Import because Dynamic SS is present under a Normal model. Working Fine in other firms.
Firm 1100 -> Model grid -> Select model ID 11 , 12 ,13 -> Export model for bulk edit -> open Exportedmodel file -> Delete model ID 12 -> Edit model ID 13 -> change subclass name from FFF to DDD -> Save Exported file -> Models grid -> Import model -> select file no. 2 -> create model. | structure of every models that contain node Edited node should be changed. | Getting Error 502 , And model structure of model ID 12 is changed. | PASS | https://docs.google.com/spreadsheets/d/1JNAf3Gq0tghjZoa6s-jMl3ZqyUFu9u5rlDns5F3rlZE/edit#gid=1065929165 | File no. 1 | Fixed | Reproduced in Firm 1300
again change DDD to FFF and FF to DD -> save file -> Import file. |  | FFF node remove from model CD | PASS | https://docs.google.com/spreadsheets/d/1NtmJmuX-xGxk0BkyfrCgemD7DK-dSTM2TIxuSM7M7E0/edit#gid=0 | File no. 2
Firm 1100 -> Create a file with multiple models ID 388 , 394 with the same class - 'Fixed C Category 1' under different categories > Set the Target Percent of this class to differ in both models > Import model file -> Create model. | [5 empty] | this is because of the updateOtherModel. In this process if we have same structure of two models than on changing one model that change get automatically refelected on another model's structure
Firm 144600 -> select models -> Export models for bulk edit -> select model ID 489 -> change security set to American Funds Growth for both node -> save file -> Models grid -> Actions -> Import model -> create model -> Check Import Logs error. | It should generate an error for Model ID 489 and Import Logs error must have an error count. | All Models status is changed to Waiting for approval from Approved. | PASS | Getting error 500 : Your request can not be processed at the moment, please verify parameters https://docs.google.com/spreadsheets/d/1T-IZReNXL4YtU5fWnZ7bQslvdGzMGY38L-_EWwTN-6Y/edit#gid=1196801537 |  | Fixed
Firm 144600 -> Models grid -> select Models ID (10 to 18 ) -> Export model for bulk edit -> open exported model file -> change models name to "TestModel" -> Model namespace must be different -> set same security set to all models -> save file -> Import model -> select file -> create model -> Open models (10 to 18). | models must be successfully saved as Model name and model namespace is unique. | Working fine now. | PASS | Assigned portfolio's Analytics Failed. |  | Fixed
Firm 144600 -> Models grid -> select Models ID (10 to 18 ) -> Export model for bulk edit -> open exported model file -> change models name to "TestModel" -> Change Model namespace to "Default team" -> set same security set to all models -> sum of all security set target % must be 100 -> save file -> Import model -> select file -> create model -> Open models (10 to 18). | Model Importing should be Failed as Model name and Model namespace is same. | Not working as Expected. | FAIL |  |  | Irrelevant case
1 > Same model name -> one ss with 100 % -> different namespace -> Import 2 > Same model name -> one ss with 100 % -> default namespace -> Import > " Security set target % <> 100 %" 3 > same model name -> one ss to every model > sum of all ss is 100 % -> default namespace -> Import.
Firm 144600 -> models grid -> select model ID 7 -> Export model for Bulk edit -> Edit Exportedmodels file -> model ID 7 -> Enter differ model name for each row -> Enter security set with target 100 % -> set category and class nodes with Band/Range -> save file -> Import model for bulk edit . | Model should not be imported as model name is differ for Model ID 7. | Working fine now. | PASS | Assigned portfolio's Analytics Failed. Model imported with data > model name from 1st row Model Category or class node from 3rd row and Security set node from 2nd row. https://docs.google.com/spreadsheets/d/1OBqnGzp8M4au7gc0NgVDDZS2jJT-hVy2m9OxmOzG3Ns/edit#gid=0 | Getting {"StatusCode":400,"Message":"There was an error retrieving entity option."} | Fixed
|  | Getting Error : "Model Name AND Model ID should remain same across all rows defining a model,SECURITYSET level targetPercent <> 100,Model Name and Model Namespace should be unique" |  | Duplicate entry '6-3-7' for key 'TEMP_ZeroNodes.IDX_TEMP_ZeroNodes_rightValue_leftValue_modelId'
CASE 5 Firm 27600 > Model grid > Select all models > Export model for Bulk edit > Import file without any change > Few nodes are present at multiple places in models. | file must be imported successfully if no changes made in Exported model file. | Working fine in firm 71400 | PASS | Node: U.S. Equity - Large Cap (Strategic) is used at multiple places and its structure doesn't match Node: ETF - High Yield is used at multiple places and its target percent or Lower/Upper doesn't match > Model ID 118 , 119 , 120
Firm 36200 > Select model ID 2550 > Class node "G AA NTE Non Trad Equity" is present in model > Edit model > Set a Fixed Tolerance Band: 0 > Apply > Save model > Open Model ID 2592 > Edit model > Add Class node "G AA NTE Non Trad Equity" > Check Tol Band is null > Model Grid > Select model ID 2550 , 2592 > Export models > Import Models without any change > Getting an error "Node: G AA NTE Non Trad Equity is used at multiple places and its target percent or Lower/Upper doesn't match" |  | Band tol. is null for child node of added Class. | PASS | Node: is used at multiple places and its target percent or Lower/Upper doesn't match | not related to this ticket
CASE 3 Firm 1300 > Model grid > Select model ID 24 , 178 > Export model for bulk edit >Import file without any change > Class node "Infrastructure" present in both models with different namespace > One of them has Class Asset type. | file must be imported successfully if no changes made in Exported model file and should not give any error as class node has different namespace. | Working fine now. firm 36200 | PASS | Cannot apply more than one Class Asset Class Type to a single sub model (Infrastructure) | Fixed
CASE 1 Firm 1300 > Model grid > Select model ID 159 > Export model for bulk edit > Import file without any change > create model. | file must be imported successfully if no changes made in Exported model file. | Not working as Expected. | FAIL | securitySet name and id are not matching with any existing securitySets ,securitySet Name OR Id is not matching with any existing securitySets | data issue
CASE 7 Firm 68300 > Model grid > Select model ID 106 , 237 , 250 > Export model for bulk edit > import file without any chnge > create model. | file must be imported successfully if no changes made in Exported model file. | Working as Expected. | PASS | Asset Class does not exist. | working as expected
Dynamic Model and SS.
Firm 1300 > Model grid > Select Dynamic model > model ID 3919 > Export model for bulk edit > Edit file > Add Normal SS to model > save > Import Exported model file > create model. | File should not be imported as Normal SS is added to Dynamic model. it should generate an error "Model and Security set isDynamic flag does not match" | Working as Expected | PASS
Firm 1300 > Model grid > Select Normal model > model ID 8277 > Export model for bulk edit > Edit file > Add Dynamic SS to model > save > Import Exported model file > create model. | File should not be imported as Dynamic SS is added to normal model. | Working as Expected | PASS
Firm 1300 > Model grid > Select Dynamic model > model ID 3919 > Export model for bulk edit > Edit file > Add Dynamic SS to model > save > Import Exported model file > create model. | file must be imported successfully if no changes made in Exported model file. | Working as Expected | PASS
Model Change Approval : False Firm 2100 > Model Grid > Export model ID 9672 > Edit file > Change Model name > Save > Import model > "Model status in waiting for approval" > Pending and approved are same. | Model name should be updated when file imported successfully. | Working fine now. | PASS | Same as Case 40 | fixed
Firm 144600> Model Grid > Select model ID 322 > Edit model > Model Info > Select Following fields - Primary Product Type, Asset Class, Risk Category > Save > Select models including model ID 322 > Export model > Edit file > edit same fields for other models > Save > Import model. | Edited fields must be updated for other models also. | Not working as Expected. | FAIL | Primary Product Type not updated for other models. | not related to this ticket
Import model with Asset Class type.
Select model ID > Edit model > Click on Category node > Select Class Asset type > Save model > Export model > Import model without any change > Check Class Asset type > Again Import Original file > Check Category Asset Class type.

## Sheet2
Test Case | Expected Results | Actual Results | Status | Messages
CASE 2 - TEST > 2100 > Export Model Id - 5550 > Import it without any changes in file > Error - '2nd MAC validations failed'.
Firm 2100 -> Model grid -> Select model 5550 , 4297 , 4408 -> Actions -> Export model for bulk edit. | It should Export model successfully as model is Approved. | Not working as Expected. | FAIL | Getting 422 Error when Exporting model file. "Update process is in progress. Please try after some time." | not reproducing
CASE 5 - TEST > 51500 > Create a file with multiple models with the same class - 'Firm - US Small Cap Value' under different categories > Set the Target Percent of these classes to differ in all models > Error - 'Node: Firm - US Small Cap Value is used at multiple places and its target percent or Lower/Upper doesn't match'. |  |  |  |  | not reproducing
|  | Not working as Expected. | FAIL | Error Node: Firm - Real Estate is used at multiple places and its structure doesn't match
CASE 6 - During bulk export - models with Status - Waiting for Approval were getting exported.
|  | Not working as Expected. | FAIL | Getting 422 Error when Exporting model file. "Update process is in progress. Please try after some time."
CASE 7 - TEST > 51500 > Export Model Id - 9717 > Import it without any changes in the file > Error - 'Asset Class does not exist'. |  | Working as Expected. | PASS
Same as Above -> Export Model ID 12871 after importing model Id 9717 file. |  | Not working as Expected. | FAIL | {StatusCode: 400, Message: "There was an error retrieving entity option."}
CASE 8 - TEST > 51500 > Import the attached file - TEST_51500_modelNameError > Error - 'Model Name and Model Namespace should be unique'.
|  | Not working as Expected. | FAIL | 2nd MAC validations failed. {successMessage: "9 Of 146 Models failed to import."}
ADD node
Firm 1300 -> Model Grid -> select model ID 8305 -> Export model for bulk edit -> open Exported model file -> Add security set node -> Target % for parent node is sum of 100 -> save file -> Import file. | it should import file if target % is sum of 100 %. | Not working as Expected. | FAIL | 2nd MAC validations failed.
DELETE node
Firm 1300 -> Model Grid -> select model ID 8305 -> Export model for bulk edit -> open Exported model file -> Delete security set node -> Target % for parent node is sum of 100 -> save file -> Import file. | it should import file if target % is sum of 100 %. | Not working as Expected. | FAIL | 2nd MAC validations failed.
Firm 51500 -> select Model ID 2147 -> Export model for bulk edit -> open Exported model file. | It should export model details with every Category , Class , Subclass and Security set node present in it. | Not working as Expected. | FAIL | Classes , Security sets and Category M2147 fixed income is missing from Exported model file.

## Sheet3
Import model with Asset Class type.
Select model ID > Edit model > Click on Category node > Select Class Asset type > Save model > Export model > Import model without any change > Check Class Asset type > Again Import Original file > Check Category Asset Class type.
CASE 5 Firm 27600 > Model grid > Select all models > Export model for Bulk edit > Import file without any change > Few nodes are present at multiple places in models. | file must be imported successfully if no changes made in Exported model file. | Not working as Expected. | FAIL | Node: U.S. Equity - Large Cap (Strategic) is used at multiple places and its structure doesn't match Node: ETF - High Yield is used at multiple places and its target percent or Lower/Upper doesn't match > Model ID 118 , 119 , 120 | not related to this ticket
CASE 1 Firm 1300 > Model grid > Select model ID 159 > Export model for bulk edit > Import file without any change > create model. | file must be imported successfully if no changes made in Exported model file. | Not working as Expected. | FAIL | securitySet name and id are not matching with any existing securitySets ,securitySet Name OR Id is not matching with any existing securitySets | data issue