## Sheet1
https://orion-advisor.atlassian.net/browse/INVST-11210 |  | Developer - Prerna, Pankaj |  | QA - Gourav Singh
Test case | Expected Result | Actual Result | Status | Message | Developer's Remark | Bug Rating
Holding
Default Preference
Firm 8500 > Pref > Firm > Add security JPM > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Default ) > Save > Portfolio grid > PID 31980 > Trade tool > TT > create trade for security. | Preference should be considered when trades validated from Tactical and TLH tool. | Working as Expected. | PASS
Firm 8500 > Pref > Firm > Add security > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for Taxable ( Default ) > Save > Portfolio grid > Trade tool > TT > create trade for security. | Preference should be considered when trades validated from Tactical and TLH tool. | Working as Expected. | PASS
Do Not Buy/Sell
Firm 8500 > Pref > Firm > Add security BAX > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy/Sell ) > Save > Portfolio grid > Trade tool > TT > create trade for security BAX. | Preference should be considered when trades validated from Tactical and TLH tool and trade discarded if Do not Buy/Sell is set. | Working as Expected. | PASS
Same as Above > Sell All > Check trade. |  | Working as Expected. | PASS
Exclude security BAX. Tactical Tool > Holding and trade details > Filter > Show excluded holdings > Buy BAX > Create trade for security. | Trade should be discarded with error message. | Working as Expected. | PASS
Add BAX as Eq. or Alt. > create trade. |  | Working as Expected. | PASS
Firm 8500 > TT > PID 31980 > Add security BAX for OASTESTING.25051 > Create Buy trade > save > Process trade > TT > create another BUY trade for same > save > Pref. > Firm > Add security VOO > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy/Sell ) > Save > Order grid > Select Trade for security BAX > Edit Order amount. | Warning message should be appear when Editing trade Amount of security and row updated with warning message at order grid and trade in pending should not be updated. | Working as Expected. | PASS
Update Amount /Shares
Add pref. for Taxabl ( Do Not Buy/Sell ) : BAX Firm 8500 > TT > PID 14403 > Add security BAX for OASTESTING.23125 > Create Buy trade > save > Pref > Firm > Add security BAX > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy/Sell ) > Save > Order grid > Select Trade for security BAX > Edit Order amount By Right Click. | Warning message should be appear when Editing trade Action of security and row updated with warning message at order grid. | Working fine now. Trade created for updated amount. | PASS |  | Existing issue , because of spelling mistake of a variable | -1
Same as Above > Open TT > Click on Save button > check order grid for Trade. | Open trades should be validated again and disacrded with warning message if any restriction set on security. | Enable trade changed to Disabled trade with Error message and 0 amount. | PASS
Same as Above > Open TT > Create trade for another security > check Open trades for securities with restrictions > Click on Save button > check order grid for Trade. | Trade should be discarded for securities with do not Buy/Sell pref when another securities trade validated in TT. | Working as Expected. | PASS
Same as Above > Remove pref. for BAX > Save > TT > Create trade for another security GOOG > check Open trades for BAX. | Trade should not be discarded for security BAX when another securities trade validated in TT. | Working as Expected. | PASS
Same as Above > Remove pref. for BAX > Save > TT > Create trade for another security GOOG > check Open trades for BAX > Order grid > Select trade for BAX > Edit Order > Enter. | Warning message should not be appear when Editing trade Amount or Action of security and Error message removed from order grid after trade edited. | Working as Expected. | PASS
Add pref. for TD and TE ( Do Not Buy/Sell ) : TestMF32.41 Firm 8500 > Pref > Firm > Add security TestMF32.41 > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy ) > Save > PID 14403 > AID OASTESTING.23125 > Trade tool > TT > create SELL trade for security TestMF32.41 > Disacrded with 0 amount and Error > Save > Order grid > select trade > Double click on Amount > Enter 2000 > Enter > Check value > Enable Trade. OR Enable and Edit trade. | Warning message should be appear when Editing trade Action of security and row updated with warning message at order grid. | Working fine now. Trade Edited without any warning message. | PASS |  | same as case 19 | -1
Add pref. for TD and TE ( Do Not Buy/Sell ) : TestMF32.41 Firm 8500 > Pref > Firm > Add security TestMF32.41 > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy ) > Save > PID 14403 > AID OASTESTING.23125 > Trade tool > TT > create BUY trade for security TestMF32.41 > Disacrded with 0 amount and Error > Save > Order grid > select trade > Double click on Amount > Enter 2000 > Enter > Check value > Enable Trade. OR Enable and Edit trade. | Warning message should be appear when Editing trade Action of security and row updated with warning message at order grid. | Working as Expected. | PASS
Update Action
Add pref. for TD and TE ( Do Not Buy/Sell ) : TestMF15.4 Firm 8500 > Pref > Firm > Add security TestMF15.4 > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy ) > Save > Portfolio grid 14403 > AID OASTESTING.23125 > Trade tool > TT > create SELL trade for security TestMF15.4 > Order grid > select trade > right click > Edit Order > Update Action from SELL to BUY > Save. | Warning message should be appear when Editing trade Action of security and row updated with warning message at order grid. | Working as Expected. | PASS
Add pref. for TD and TE ( Do Not Buy/Sell ) : TestMF15.4 Firm 8500 > Pref > Firm > Add security TestMF15.4 > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy ) > Save > Portfolio grid 14403 > AID OASTESTING.23125 > Trade tool > TT > create SELL trade for security TestMF15.4 > Order grid > select trade > right click / Double click > Edit Order > Update Action from SELL to BUY > Save. | BuyPriority Warning message should be appear when Editing trade Action from Sell to Buy of security and row updated with warning message at order grid. | Working as Expected. | PASS
Add pref. for TD ( Do Not Buy/Sell ) : MSFT Firm 8500 > Pref > Firm > Add security MSFT > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD ( Do Not Buy ) > Save > Portfolio grid PID 31980 > AID OASTESTING.24887 (TD) , OASTESTING.25051 (TE) > Both have holding of MSFT > Trade tool > TT > create SELL trade for security MSFT for TD > check trade and error message. | Trade should be discarded with error message. | Working as Expected. | PASS
Same as above > Enter positive and negative Amount in Trade $ and share column. | Trade should be discarded with error message. | Working as Expected. | PASS
Same as above > Enter amount in Buy $ column.
Same as above > Enter amount in Sell $ column.
Add pref. for TD ( Do Not Buy/Sell ) : MSFT Firm 8500 > Pref > Firm > Add security MSFT > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD ( Do Not Buy ) > Save > Portfolio grid PID 31980 > AID OASTESTING.24887 (TD) , OASTESTING.25051 (TE) > Both have holding of MSFT > Trade tool > TT > create SELL trade for security MSFT for TE > check trade and error message. | Trade should be created without any warnig message. | Working as Expected. | PASS
Same as above > Enter positive and negative Amount in Trade $ and share column. | Trade should be discarded with error message. | Working as Expected. | PASS
Same as above > Enter amount in Buy $ column.
Same as above > Enter amount in Sell $ column.
TLH - Taxable Account
Add pref. for T, TD and TE ( Do Not Buy/Sell ) : BAX Firm 8500 > Acc.Number 48820175 > TLH > Automated > Short and Long term > Select All security > Add Buy security BAX > validate all > check error message. | Trade should be discarded wth Error message when trade validated in TLH. | Working fine now. Trade validated without any warning message in TLH. | PASS |  | same as case 19 | -5
Same as above > Calculate validated trades > Order grid > check trades and Message. | Trade should not be created. | Working fine now. Trade created without any message. | PASS
Bulk Testing Add pref. for T, TD and TE ( Do Not Buy/Sell ) : BAX Firm 8500 > Portfolio grid > Dashboard filter > TLH opp. > Select all portfolios 7903 > TLH > Automated > Short and Long term > Select all rows 76,388 > Buy TLH alt BAX (Do not Buy Sell for T, TD ad TE) > Validate. Trade discarded for 70,470 rows while Trade validated for remaining rows without any warning Select Validated rows > Again Validate > > Trade Discarded with error message | Trade should be discarded wth Error message when trade validated in TLH. | Trade discarded for 70k rows while validated for remaining rows. 12 batches 11:22 mins OR Trade validated for BAX without wanirng where Any warning appear for Sell security | FAIL |  | existing
Bulk Testing Add pref. for T, TD and TE ( Do Not Buy/Sell ) : BAX Firm 8500 > Portfolio grid > Dashboard filter > TLH opp. > Select all portfolios 7903 > TLH > Automated OR (Manual / Loss) > Short and Long term > Select rows 26,072 > Buy TLH alt BAX (Do not Buy Sell for T, TD ad TE) > Validate. | Trade should be discarded wth Error message when trade validated in TLH. | Working as Expected. | PASS
Add pref. for T, TD and TE ( Do Not Buy/Sell ) : BAX Firm 8500 > Acc.Number 48820175 > TLH > Automated > Short and Long term > Select Buy security TestMF32.41 > Add Buy security BAX > validate all > check error message. | Trade should be discarded for Sell security with Error message when trade validated in TLH. | Working as Expected. | PASS
Add pref. for T, TD and TE ( Do Not Buy/Sell ) : MSFT and BAX Firm 8500 > Acc.Number 48820175 > TLH > Automated > Short and Long term > Select Sell security MSFT > Add Buy security BAX > validate > check error message. | Sell trade should be discarded wth Error message when trade validated in TLH. | Working as Expected. | PASS
Add pref. for T, TD and TE ( Do Not Buy/Sell ) : TestMF15.4 and TestMF32.41 Firm 8500 > No Pref set > Acc.Number REBALTEST1 > TLH > Automated > Short and Long term > Select Sell security TestMF15.4 > Add Buy security TestMF32.41 > validate > check error message > Calculate > Order grid > Firm pref > Set Pref for Buy and Sell security > Save > Run Analytics > Order grid > Select security > Edit Order By Double Click > Amount or Qty > Ok > Save > check waning message in Popup and Order grid. | Warning message should be appear when Editing trade Amount and Action of security and row updated with warning message at order grid. | Warning message does not appear for both security at order grid. | FAIL |  | existing issue, we can edit trades on the order grid using either right-click or double-click, but both methods behave differently. When editing by double-click, the value is not being stored in the respective table for the warning message. However, editing via right-click works as expected.
Edit Order by Right Click. |  | Working as Expected. | PASS
Quick trade Firm 8500 > Order grid > Quick trade > Acc. ID OASTESTING.23124 > Buy > TestMF32.41 > OR Sell > TestMF15.4 > Validate > Add trade. | Error message should appear when validate trade and Trade discarded with message at order grid. | Working as Expected. | PASS
Lots
Firm 8500 > Pref > Firm > Add security TestMF15.4 > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy/Sell ) > Save > Portfolio grid 14403 > Trade tool > TT > Select security TestMF15.4 > Filter lots > create Sell trade for taxlots. | Trade should be discarded with error message. | Working as Expected. | PASS
Firm 8500 > Pref > Firm > Add security TestMF15.4 > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy/Sell ) > Save > Portfolio grid 14403 > Trade tool > TT > Holdings > Select security TestMF15.4 > Create Buy trade > Check Warning message > Filter lots > create Sell trade for taxlots > check warning message for taxlot. | Do not Buy wanirng message should appear for Dummy taxlot and Do not Sell warning for original taxlot when trade created. | Working as Expected. | PASS
Same as above > holding Check wanring message. | Both warning message appear for holding as security trade created for Buy and Sell. | Working as Expected. | PASS
VSP : ON
Firm 8500 > Pref > Firm > Add security TestMF15.4 > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy/Sell ) > Save > Portfolio grid 31980 > Trade tool > TT > Select security TestMF15.4 > Filter lots > create Sell trade for taxlots > Order grid > Edit Taxlot > check warning message. | Warning message should be appear when Editing trade Action of security and row updated with warning message at order grid. | Working as Expected. | PASS
Override Restrictions in Tactical and Quick Trades : Enable | Trade created with Warning message in Tactical Tool. | Working as Expected. | PASS
Split Flag : account_tax_type_preferences_s11210 : ON / OFF |  | Working as Expected. | PASS
Review App
Review App > Prefrences > Firm level > Security pref. > Search secuirty > AGG > Scroll down > Find Option "Trade Settings By Account Type ( Do Not Buy/Sell )" > Set restriction Do not Buy/Sell for Taxable , TD and TE account > Save. | Pref should be saved. | Working as Expected. | PASS
Review App > Firm 8500 > PID 19196 > AID OASTESTING.24889 (TD) Security AGG and TLT (Do Not Buy / Sell) , MSFT (Do not Sell ) , JPM (Do not Buy).
Tactical Tool > Holding and trade details > Buy AGG , TLT or JPM , Or Sell MSFT and others. | Preference should be considered when trades validated from Tactical and TLH tool and trade discarded if Do not Buy/Sell is set. | Working as Expected. | PASS
Exclude security AGG. Tactical Tool > Holding and trade details > Filter > Show excluded holdings > Buy AGG > Create trade for security. | Trade should be discarded with error message. | Working as Expected. | PASS
Add AGG as Eq. or Alt. > create trade. |  | Working as Expected. | PASS
Tactical Tool > Holding and trade details > Buy AGG , TLT or JPM , Or Sell MSFT and others > Save trades > Order grid > check trades and warning. | Discarded trade created on order grid. | Working as Expected. | PASS
Edit trade amount / Quantity or Action.
Tactical Tool > Holding and trade details > Buy AGG > Save trades > Order grid > check disable trade > Amount/Qty > Double click > Update amount/Qty > check popup warning > ok > Check trade and warning > compare with Tactical tool. | Warning message should be appear when Editing trade Action of security and row updated with warning message at order grid. | Working as Expected. | PASS
Tactical Tool > Holding and trade details > Buy AGG > Save trades > Order grid > check disable trade > Amount/Qty > Right click > Edit order > Update amount/Qty > check popup warning > ok > Check trade and warning > compare with Tactical tool. | Warning message should be appear when Editing trade Action of security and row updated with warning message at order grid. | Working as Expected. | PASS
Tactical Tool > Holding and trade details > Buy AGG > Save trades > Order grid > check disable trade > Amount/Qty > Right click > Edit order > Update Action (Sell to Buy or vice versa) > check popup warning > ok > Check trade and warning > compare with Tactical tool. | Buy or Sell Warning message should be appear when Editing trade Action of security and row updated with warning message at order grid. | Working as Expected. | PASS
Tactical Tool > Holding and trade details > JPM > Perform below operations.
Same as above > Enter positive and negative Amount in Trade $ and share column. | Trade should be discarded with error message. | Working as Expected. | PASS
Same as above > Enter amount in Buy $ column.
Same as above > Enter amount in Sell $ column.
Lots
Firm 8500 > Pref > Firm > Add security AGG > Set pref. > Trade Settings By Account Type ( Do Not Buy/Sell ) > Add pref. for TD and TE ( Do Not Buy/Sell ) > Save > Portfolio grid 19196 > Trade tool > TT > Holdings > Select security AGG > Create Buy trade > Check Warning message > Filter lots > create Sell trade for taxlots > check warning message for taxlot. | Do not Buy wanirng message should appear for Dummy taxlot and Do not Sell warning for original taxlot when trade created. | Working as Expected. | PASS
Same as above > holding Check wanring message. | Both warning message appear for holding as security trade created for Buy and Sell. | Working as Expected. | PASS
Review App > Firm 8500 > PID 21273 > AID OASTESTING.25051 (TE) Security ITOT and VOO (Do Not Buy / Sell) | Preference should be considered when trades validated from Tactical and TLH tool and trade discarded if Do not Buy/Sell is set.
Check above cases. |  | Working as Expected. | PASS
Review App > Firm 8500 > PID 19192 > AID OASTESTING.24881 (T) Security AGG and TLT (Do Not Buy / Sell) | Preference should be considered when trades validated from Tactical and TLH tool and trade discarded if Do not Buy/Sell is set.
Check above cases. |  | Working as Expected. | PASS
Firm 8500 > PID 19192 > TLH > Automated > Short and Long term > Select any Sell security > Buy TLT > Validate > check warning message. | Trade should be discarded wth Error message for restricted security when trade validated in TLH. | Working as Expected. | PASS
Select Sell Security AGG > Buy any > Validate. |  | Working as Expected. | PASS
Select All secuirty > Buy AGG or TLT >validate. |  | Working as Expected. | PASS
Bulk Testing Add pref. for T, TD and TE ( Do Not Buy/Sell ) : AGG Firm 8500 > Portfolio grid > Dashboard filter > TLH opp. > Select all portfolios 7993 > TLH > Automated > Short and Long term > Select all rows 81,000 > Buy TLH alt AGG (Do not Buy Sell for T, TD ad TE) > Validate. | 12 batches - 81000 rows | Getting error 502. https://pr117078.reviewapps.run/v1/tradetool/taxLossHarvesting/action/validateTLHSecurities | FAIL |  | not able to reproduce
Same as above. | 4 batches - 38000 rows
Split Flag : account_tax_type_preferences_s11210 : ON / OFF |  | Working as Expected. | PASS
Security BA, MSFT and VOO are TLH alts to TLT. (All Buy Alts are Do not Sell / Buy ) Review App > Firm 8500 > PID 19192 > AID OASTESTING.24881 > TLH > Automated > Short and Long term > Select Security TLT > Validate. | Trade should be discarded for Buy message with Error message for all buy alts. | Trade created for MSFT (got error for BA) > Again validate same > Trade created for BA (Got message for MSFT). | FAIL